## Stage1 Audit Findings & Tracker
Security Assessment Stage 1 (Initial Audit) Findings |  |  |  |  | Inputs from EU TechOps Team on Patching |  | Security Assessment Stage 1 (Post Revalidation Audit) Status
Sr. No. | Vulnerability Name | Vulnerable Point, Port or Parameter | Overall Risk (Severity) | Mapping with OWASP Testing Checklist | Action Taken | Remarks (If any) | Post Revalidation Audit Status | Vulnerability Status Post Revalidation Audit | Status
1 | Swagger API Disclosure | https://amritdemo.piramalswasthya.org/flw-0.0.1/swagger-ui.html https://amritdemo.piramalswasthya.org/tmapi-v1.0/swagger-ui.html | Medium | OWASP - Insecure Authentication Testing | Taken |  | Completed | Unresolved
2 | Improper Session Management | https://amritdemo.piramalswasthya.org/identity-0.0.1/rmnch/syncDataToAmrit | Medium | OWASP - Session Management Testing | Taken |  | Completed | Unresolved
3 | Sensitive User Information available inside Unencrypted Shared Preferences | /data/data/﻿org.piramalswasthya.sakhi/shared_prefs # cat Sakhi-pref-1.xml | Medium | OWASP Insecure Data Storage Testing | Taken |  | Completed | Resolved
4 | Extraneous Functionality | Application Logs | Medium | OWASP Extraneous Functionality Testing | Taken |  | Completed | Unresolved
5 | Improper Platform Usage - Debuggable | Androidmainfest.xml | Medium | OWASP - Improper Platform Usage Testing | Taken |  | Completed | Resolved
| - ClearText Traffic |  |  |  | Taken |  | Completed | Resolved
6 | Sensitive Information Data | https://amritdemo.piramalswasthya.org/commonapi-v1.0/user/userAuthenticate/ | Medium | OWASP - Configuration and Deploy Management Testing | Taken |  | Completed | Unresolved
7 | Task Switching | Android Application | Low | OWASP - Security Misconfiguration Testing | Taken |  | Completed | Resolved
8 | CORS | https://amritdemo.piramalswasthya.org/tmapi-v1.0/registrar/registrarBeneficaryRegistrationNew | Low | OWASP - Client Side Testing | Taken |  | Completed | Unresolved
9 | Copy Paste Buffer | Android Application | Low | OWASP - Configuration and Deploy Management Testing | Taken |  | Completed | Unresolved
10 | Lack of code obfuscation | Org.piramalswasthya.sakhi/cryptoUtil Org.piramalswasthya.sakhi/database/room/dao/BeneficaryIdsAvailDao_Impl Org.piramalswasthya.sakhi/database/room/InAppDb Org.piramalswasthya.sakhi/database/room/InAppDb_Impl | Low | OWASP Reverse Engineering Testing | Taken |  | Completed | Unresolved
11 | APP runs on Rooted Device | Root Detection Mechanism | Low | OWASP – Reverse Engineering Testing | Taken |  | Completed | Unresolved
Android Mobile related
AMRIT backend related
AMRIT backend related
| Swagger API Disclosure | it's an open source, can be public, Turn it off from Prod Build (remove)
| CORS | sachin/ srinivas - wilfy configuration
| Improper Session Management | auth Token, Refresh Token (User Login) -