## Sheet1
S.No | Module Name | Test Scenario | Step to Execute | Expected Result | To be test By | Status of 5.0.4 | Actual Results | Remark
1 | CHO Tab | Data Sync Issue | Login → Go to CHO tab → Try syncing data → Navigate to Lab Technician tab | Data should sync properly and allow navigation to Lab Technician tab | QA | Fixed | Data is now syncing correctly and navigation to Lab Technician tab is working | Issue resolved
2 | CHO Tab | Duplicate Patient Entries | Register a patient → Go back to CHO tab → Check entries | Only one entry should be visible per registration | QA | Fixed | Duplicate entries are no longer appearing | Issue resolved
3 | CHO Tab | Edit Patient Details | Register patient → Submit → Try editing details | User should be able to edit and resubmit details | QA | Fixed | Edit functionality is now working | Issue resolved
4 | Lab Technician Tab | Procedures Not Visible | Add lab investigation → Go to Lab Technician tab | Added procedures should be visible | QA | Fixed | Procedures are now visible after adding lab investigations | Issue resolved
5 | Pharmacy Tab | Line Listing Missing | Complete patient flow → Go to Pharmacy tab | Line listing should be displayed | QA | Fixed | Line listing is now appearing correctly | Issue resolved
6 | Login & Logout Flow | User Login and Logout Functionality | Open app → Enter valid credentials → Login → Navigate through app → Logout | User should login successfully and logout should clear session and redirect to login screen | QA | Already Working | Login and logout are working correctly, session is cleared on logout | Already working

## Sheet2
S.No | Module Name | Test Scenario | Step to Execute | Expected Result | To be test By | Status of 5.0.6 | Actual Results | Remark
1 | Registration / ABHA | ABHA Option Not Responding | Register beneficiary → Click on ABHA option | ABHA option should respond and proceed further | QA | Fixed | ABHA option is now responding correctly after registration | Issue resolved
2 | CHO Tab | Chief Complaint Missing (Diabetes & Hypertension) | Login → Go to CHO tab → Open Chief Complaint section | Diabetes and Hypertension options should be visible | QA | Fixed | Diabetes and Hypertension are now visible in Chief Complaint section | Issue resolved
3 | Pharmacy Tab | Pharmacy Module Not Working | Complete patient flow → Navigate to Pharmacy module | Pharmacy module should function properly with all actions | QA | Fixed | Pharmacy module is now working as expected | Issue resolved
4 | Lab Technician Tab | Test Result Options Missing | Add lab test → Go to Lab Technician tab → Try adding results | All test result options should be available (not only haemoglobin) | QA | Fixed | All test result options are now available in Lab Technician module | Issue resolved
6 | Login & Logout Flow | User Login and Logout Functionality | Open app → Enter valid credentials → Login → Navigate through app → Logout | User should login successfully and logout should clear session and redirect to login screen | QA | Already Working | Login and logout are working correctly, session is cleared on logout | Already working